## Slide 1: Quality Matters Training for Faculty at RPCC
River Parishes Community College

## Slide 2: Project Summary
Fall 2015-Spring 2017: Faculty at RPCC wishing to teach online completed various Quality Matters courses (Board of Regents Grant Contract Number LEQSF(2015-16)-ENH-PEN-13)
Spring 2017: LCTCS announced merger of RPCC and South Central Louisiana Technical College – Reserve campus.
Merger created a training divide, so this grant sought, in part, to offer training in online course design to new RPCC faculty members
Influx of online classes to be reviewed created a need for additional QM Peer Reviewers to serve on institutional service committee, Online Course Evaluation Committee
Some of our mature online courses were put through a full QM review to earn a Quality Matters Certification Mark

## Slide 3: OER
Our chancellor, Dr. Dale Doty, announced a “Textbook Free by 2023” initiative to reduce costs for students
Priority was given to our OER online courses for full QM review

## Slide 4: Goals
Goal 1: Continue training for new online faculty at RPCC in the best practices of online pedagogy using QM Professional Development workshops
Goal 2: Expand the number of certified Peer Reviewers who serve on the Online Course Evaluation Committee
Goal 3: Complete Subscriber-Managed QM Reviews for online courses to receive the QM Certification Mark. Priority given to OER online courses

## Slide 5: Objectives
Objectives for Goal 1: At least 10, but no more than 40 of RPCC’s new faculty members from the Gonzales and Reserve campuses will be trained in the QM Designing Your Online Course workshop and/or the QM Improving Your Online Course workshop.
  Currently, 23 faculty members have completed or are scheduled to complete these workshops
Objectives for Goal 2: At least 1, but no more than 5 of RPCC’s new faculty members from the Gonzales and Reserve campuses will be trained in a QM workshop to learn how to be reviewers of online courses.
  3 faculty members completed in the QM Peer Reviewer Workshop
Objectives for Goal 3: At least 1, but no more than 3 of RPCC’s current online courses will undergo a complete QM Subscriber-Managed Review to earn a QM Certification Mar.
  3 of RPCC’s OER online courses have undergone the full QM review. 2 courses passed review without revision, and the third is currently under revision.